## Project Plan
PROJECT GANTT CHART — AI Insurance Survey Agent
Duration: 10 Months (Jan 6, 2025 – Oct 31, 2025) ¦ 43 Weeks ¦ Last Updated: Mar 2025
[6 empty] | Jan 2025 |  |  |  | Feb 2025 |  |  |  | Mar 2025 |  |  |  |  | Apr 2025 |  |  |  | May 2025 |  |  |  | Jun 2025 |  |  |  | Jul 2025 |  |  |  |  | Aug 2025 |  |  |  | Sep 2025 |  |  |  | Oct 2025
# | Task / Deliverable | Owner | Start | End | % Done | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43
Phase 1: Core Pipeline Modules (M0–M7)
1 | Project Setup & Infrastructure | Team | 06 Jan 2025 | 19 Jan 2025 | 100%
2 | M0: Quality Gate & PII Masking | Team | 20 Jan 2025 | 16 Feb 2025 | 100%
3 | M1: Fraud Detection (EfficientNet-B4) | Team | 03 Feb 2025 | 02 Mar 2025 | 100%
4 | M2: Vehicle Identification (YOLOv10) | Team | 03 Mar 2025 | 30 Mar 2025 | 80%
5 | M3: Part Segmentation (SegFormer-B5) | Team | 17 Mar 2025 | 13 Apr 2025 | 60%
6 | M4: Damage Analysis (Dual-Model) | Team | 14 Apr 2025 | 11 May 2025 | 0%
7 | M5: 3D Depth Estimation | Team | 12 May 2025 | 01 Jun 2025 | 0%
8 | M6: ICVE Pricing Engine | Team | 12 May 2025 | 08 Jun 2025 | 0%
9 | M7: Report Generator (VLM) | Team | 09 Jun 2025 | 29 Jun 2025 | 0%
10 | Phase 1 Integration & Testing | Team | 16 Jun 2025 | 06 Jul 2025 | 0%
Phase 2: Research Contributions
11 | RAG Knowledge Layer (pgvector) | Team | 07 Jul 2025 | 03 Aug 2025 | 0%
12 | Cross-Training Data Flywheel | Team | 04 Aug 2025 | 31 Aug 2025 | 0%
13 | Drift Detection & MLOps | Team | 01 Sep 2025 | 28 Sep 2025 | 0%
14 | Research Paper & Advanced Features | Team | 29 Sep 2025 | 19 Oct 2025 | 0%
15 | Final Integration, Docker & Delivery | Team | 06 Oct 2025 | 31 Oct 2025 | 0%
Documentation & Milestones
16 | Weekly Status Reports | Team | 06 Jan 2025 | 31 Oct 2025 | 30%
17 | Monthly Review Reports | Team | 31 Jan 2025 | 31 Oct 2025 | 20%
18 | Feature Spec & Design Documents | Team | 06 Jan 2025 | 02 Mar 2025 | 100%
19 | Test Cases Documentation | Team | 14 Apr 2025 | 31 Oct 2025 | 0%
20 | User Manual & Reusable Assets | Team | 01 Sep 2025 | 31 Oct 2025 | 0%
21 | Final Executables & Repo Publish | Team | 20 Oct 2025 | 31 Oct 2025 | 0%
LEGEND
Completed (100%)
Phase 1 — Core Pipeline
Phase 2 — Research
Milestone / Integration
Final Delivery
Ongoing Documentation